## Weekly Build
Team Hyjak Build Acceptance Checklist | [7 empty] | Milestone | Week: | Semester: | Version: | [6 empty] | David Hedner | Ryder Claus | None | None | None | Inactive | None
[8 empty] | 6 | 14 | 2 | 21 | [6 empty] | Lorenzo St. Luce | Dylan Barlow | David Hedner | Production | Documents/Rubric | Week | Pass
Reminders: - BE CAREFUL USING [Ctrl] + [X/C/V] TO CUT, COPY OR PASTE CELLS. This will damage the conditional formatting of the document. - Creating a new row requires manually fixing the completion formulas that column (A) relies on. - The layout and operations of this spreadsheet come from the provided template and ARE NOT COMPLETE. Future iterations of data, interface, and formulas will be improved to better serve our team. - Start with setting the "Week" column (B) to "Week", then the "#" column (C) to the current week number - Note that once "Week" is set, the row will turn red and stay red until the right week number is set - Verification will likely be carried out by production or QA, but observable verification can be done by any discipline. - ALL disciplines are allowed to fill items marked as "Production" | [17 empty] | Avery Steines | 1 | Lorenzo St. Luce | Design | Content/Asset | Divider | Partial
New/Missing/Changed Items: |  |  | Changes are described in-depth in the weekly build notes | [14 empty] | Justin Jackson | Arthur Wroblewski | Avery Steines | Tech | Feature/Mechanic | Past Week | Fail
| Week | # | Requirement Type | Item Name | Description of Item | Ver. # | Location | Creator of Item | Discipline of Item | Verification Preferably a Lead, QA, or Producer |  |  |  | Test 2 Tester preferably of a DIFFERENT discipline |  |  |  | Harley Kirby | Aviral Gusain | Justin Jackson | Art | Data/Balancing |  | Missing
[10 empty] | Results | Tester Name | Date and Time | Notes | Results | Tester 2 | Date and Time 2 | Notes 2 | Irene Leung | Javi Morales Cortes | Harley Kirby | Audio |  |  | Overruled
0 | Divider |  |  |  | Weekly Build: | [12 empty] | Wei-No Wu | Kip George | Irene Leung | Quality
2 | Week | 14 | Documents/Rubric | Build Acceptance Test | This document is fully up to date and fully tested for the current build submission. | 1.0.0 | Teams >> Builds >> Week [*] >> Week [*] Build.zip >> BuildAcceptanceChecklist.xlsx | David Hedner | Production | Pass | David Hedner | 2025-04-15 20:00 | The build used to complete this checklist is 83584 which is the build we are submitting. (Used by Wei-No Wu and Irene Leung) | [6 empty] | Wei-No Wu
2 | Week | 14 | Documents/Rubric | Build Notes | Notes accurately reflect the project state and build changes per the indicated Perforce commit ID. | 1.0.0 | Teams >> Builds >> Week [*] >> Week [*] Build.zip >> BuildNotes.docx | David Hedner | Production | Pass | David Hedner | 2025-04-15 20:00 | Build notes have been written with accurate descriptions of new content for the build. | [5 empty] | Dakota Zander | Ryder Claus
2 | Week | 14 | Documents/Rubric | Weekly Build | Project builds and runs as intended per the Build Instructions and indicated Perforce commit ID. (Weekly Build not needed for M6, but is submitted to Teams like usual anyway.) | 1.0.0 | Teams >> Builds >> Week [*] >> Week [*] Build.zip | David Hedner | Production | Overruled | David Hedner | 2025-04-15 20:00 | It is in the correct folder and with the correct Revision ID (83584). | [5 empty] | Annika Trautwein | Dylan Barlow
0 | Divider | 12 |  |  | Built Acceptance Checklist: | [13 empty] | Modem Bumrungkhet | Adam Lonstein
2 | Week | 14 | Documents/Rubric | Week & Milestone Updated | Updated milestone and week number in this sheet, including cells G2, H2, and column C. | 1.0.0 | Teams >> Weekly Build Acceptance Test.xlsx | David Hedner | Quality | Pass | David Hedner | 2025-04-15 20:00 | Currently in week 14, M6 | [5 empty] | Bryce Fisher | Arthur Wroblewski
2 | Week | 14 | Documents/Rubric | QA Checklist Revision | Build Acceptance Checklist reflects the current build number. | 1.0.0 | Teams >> Weekly Build Acceptance Test.xlsx | David Hedner | Quality | Pass | David Hedner | 2025-04-15 20:00 | The build used to complete this checklist is 83584 which is the build we are submitting. (Used by Wei-No Wu and Irene Leung) | [5 empty] | Ethan Chen | Aviral Gusain
2 | Week | 14 | Documents/Rubric | QA Checklist New Assets | All new features and contents have been added to the QA checklist and categorized properly. | 1.0.0 | Teams >> Weekly Build Acceptance Test.xlsx | David Hedner | Quality | Pass | David Hedner | 2025-04-15 20:00 | The checklist contains all the new features the team added for week 14, M6 | [5 empty] | Anthon Reid | Kip George
0 | Divider | 14 |  |  | Menus: | 1
2 | Week | 14 | Content/Asset | Main Menu Title | Main Menu displays the game title. | 1.0.0 | Unreal >> Main Menu | None | Design | Pass | Irene Leung | 2025-04-15 20:00 | New game logo has been added | [6 empty] | Dakota Zander
2 | Week | 14 | Content/Asset | Main Menu | Main menu is on top of an animated game scene. | 1.0.0 | Unreal >> Main Menu | None | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | [7 empty] | Annika Trautwein
2 | Week | 14 | Content/Asset | Start Game Sequence | Upon starting game, a camera sequence should play. | 1.0.0 | Unreal >> Main Menu | None | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Documents/Rubric | Splash Screen | Splash screen is scaled properly and shows for an approriate amount of time. Displays DigiPen logo, Unreal, Wwise and Hyjak | 1.0.0 | Unreal |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | Splash screen includes Unreal, DigiPen, and Wwise copyright | [6 empty] | Modem Bumrungkhet
2 | Week | 14 | Content/Asset | Pause Menu | Pause Menu is accessed from pressing [ESC] in game, with functioning buttons | 1.0.0 | Unreal |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | [7 empty] | Bryce Fisher
2 | Week | 14 | Content/Asset | Option Menu | Option menu is functional and accessed through pause menu. Can see controls from option menu | 1.0.0 | Unreal |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | [7 empty] | Ethan Chen
2 | Week | 14 | Feature/Mechanic | [ESC] on Main Menu | Pressing [ESC] in game brings up the escape menu | 1.0.0 | Unreal >> Main Menu |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | [7 empty] | Yakshin Vijay
2 | Week | 14 | Feature/Mechanic | Main Menu Feedback | Hovering over and pressing buttons shows visual feedback. | 1.0.0 | Unreal >> Main Menu | None | Design | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Menu Audio | Implemented Audio for the Main Menu, Win State, and Lose State. UI now has sound. | 1.0.0 | Unreal >> Play | Avery Steines | Audio | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Loading Screen | Loading screen plays when you get into the Main Level. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Credits Screen | Credit scene shows all creators and individuals involved. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Game Controller Screen | Game controller screens appear after splash screens and hints controller is supported. | 1.0.0 | Unreal >> Play | Irene Leung | Design | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Win/Lose Screens | When losing or winning, the appropriate screen appears. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | Win game texture and lose game texture
2 | Divider | 14 |  |  | Gameplay Systems: | 4 |  |  |  | Pass
2 | Week | 14 | Feature/Mechanic | Win State | Calling the subway at the end of the level with [F] triggers the win state | 1.0.0 | Unreal >> Play | Lorenzo St. Luce | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Lose State | Lose state can be entered by dying to enemy or pressing [J] debug cheat to decrease health to a value of 0 | 1.0.0 |  | Lorenzo St. Luce | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Score System | Score system reflects a letter grade and numeric score based on how well the player performs | 1.0.0 | Unreal >> Play | Arthur Wroblewski | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
#REF! | Divider | 14 |  |  | Gameplay UX / UI: | 4
2 | Week | 14 | Data/Balancing | Debug Information | Debug information displays for newer gameplay systems and performance data. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Enemy Lock-On UI Indicator | Implemented Enemy lock-on UI indicator | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | HUD | HUD now has working Spark Charge display, working weapon switch, and a working sprint button display | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | Fixed: Misleading button name (Options menu)
2 | Week | 14 | Content/Asset | Tutorials | Tutorials throughout the level that makes sense and helps player get through the level. Two types of tutorials are normal text tutorial, and freeze frame tutorial. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | Fixed: Spark Charge tutorial box disappearing occasionally
2 | Week | 14 | Content/Asset | Perfect Dodge VFX | Perfect dodging has a special attack | 1.0.0 | Unreal >> Play |  | Art | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Spark Charge VFX | Spark charge VFX on player. Added smooth decay of spark charge. | 1.0.0 | Unreal >> Play | Bryce Fisher | Art | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Weapon Swap Effect | Weapon swap has an updated effect | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Dynamic Music | Music transitions based on events in game | 1.0.0 | Unreal >> Play | Avery Steines | Audio | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Damage Numbers | Implemented damage numbers | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Weapon Arcs | Staff weapon has attack vfx on both ends. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Character Model | Replaced default character model to the new one | 1.0.0 | Unreal >> Play |  | Art | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Waypoints Display | In the main level, a waypoint should guide the player. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Enemy Attack Sound Effect | Enemy has Sound Effect when attacking | 1.0.0 | Unreal >> Play |  | Audio | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Enemy Health Bar | Enemy health bar scales differ based on enemy health | 1.0.0 | Unreal >> Play | Wei-No Wu | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Custom Cursor | Game uses a software cursor and changes states when hovering over UI elements. | 1.0.0 | Unreal >> Play | Wei-No Wu | Tech | Pass | Irene Leung | 2025-04-15 20:00 | Fixed: Mouse doesn’t switch to hovered sprite
2 | Week | 14 | Content/Asset | Encounter Score | After each encounter, a letter and number score will display | 1.0.0 | Unreal >> Play |  | Tech | Partial | Wei-No Wu | 2025-04-15 20:00 | Issue: Grading can appear between waves
0 | Divider | 13 |  |  | Player Character: | 4 | [6 empty] | \
2 | Week | 14 | Feature/Mechanic | Player Camera | 3rd-person camera follows the players and pivots/pans with mouse movement. Camera no longer clips with enemies. Added camera shake when the player gets hit. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Dash | Reworked dashing | 1.0.0 | Unreal >> Play | Lorenzo St. Luce | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Weapon Switch | Player can switch between weapons with [Right Click], and is able to change at anytime | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Sprinting | Player can sprint by holding down [Left Shift]. Players can now go into a sprinting mode when walking for a duration. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Player Blur Effect | Blur effect added onto the player's model when performing a perfect dodge. | 1.0.0 | Unreal >> Play |  | Art | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Footsteps audio | Footstep audio plays when player moves, footstep speed should match the animation with or without sprinting. | 1.0.0 | Unreal >> Play | Avery Steines | Audio | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Main Level Music | main level music should be dynamic and change base on combat and non-combat encounters | 1.0.0 | Unreal >> Play | Avery Steines | Audio | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Player related Audio Effects | Audio Zoo has the 5 main state music triggerable by collision hitbox. | 1.0.0 | Unreal >> Play | Avery Steines | Audio | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Player Hit | Player will now be knocked back when getting hit. | 1.0.0 | Unreal >> Play |  | Tech | Pass | David Hedner | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Player falling animation | Player has a falling animation. | 1.0.0 | Unreal >> Play |  | Art | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Player Faces Enemy | The player now faces towards the targeted enemy. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Player Spawn Location | Player spawn should be reasonable. | 1.0.0 | Unreal >> Play |  | Design | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Player Attack VFX | Player attacks have animations and VFX and SFX | 1.0.0 | Unreal >> Play |  | Art | Partial | Irene Leung | 2025-04-15 20:00 | Issue: 3rd sword attack VFX disapear / dont play Issue: On occasion SFX during freeze frame play on repeat
2 | Week | 14 | Feature/Mechanic | Player Ultimate | The player ultimate should be triggered by pressing [Space] when the spark charge bar is full. The ultimate should play an animation and transition into the actual attack. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Player Health Regeneration | Player now regains some health when attacking enemies. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Perfect Dodge | Perfect dodge now triggers easier. Should give player spark charge. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Player Death Animation | Player has a death animation when dying. | 1.0.0 | Unreal >> Play |  | Art | Pass |  | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Player Model | Player has a model with colors | 1.0.0 | Unreal >> Play |  | Art | Pass | Wei-No Wu | 2025-04-15 20:00
0 | Divider | 14 |  |  | Enemies: | 4
2 | Week | 14 | Feature/Mechanic | Enemy Staggers | Enemy staggers on hit | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Enemy Hit Reg. | Enemy On hit VFX | 1.0.0 | Unreal >> Play |  | Art | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Enemy Behavior | Enemies now have a variety of different behavior. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Enemy Detection | Enemy disconnect range | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Juggernaut Enemy | Juggernaut is the large enemy with the most health. With different attacks with animations and has a mesh. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | New meshes and rigs!
2 | Week | 14 | Content/Asset | Citizen Enemy | Citizen is the medium enemy with the most health. With different attacks with animations and has a mesh. Moves includes teleporting moves and combos. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | New meshes and rigs!
2 | Week | 14 | Content/Asset | Scrap Enemy | Scrap is the small enemy with the most health. With different attacks with animations and has a mesh. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | New meshes and rigs!
2 | Week | 14 | Feature/Mechanic | Enemy Damage | Enemies can deal different damage to the player that is reasonable. | 1.0.0 | Unreal >> Play |  | Design | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Enemy Attack | Enemy attacks now have variety. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Enemy Spawn Indicator | Enemy spawning has an indicator. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Boss Enemy | Boss enemy will now spawn in the final encounter. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | Fixed: Boss doesn't have audio. Issue: Player can be launched in final boss fight
2 | Week | 14 | Content/Asset | Boss Enemy - Model | Boss enemy has a model and textures | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
#REF! | Divider | 14 |  |  | Combat Mechanics: | 4
2 | Week | 14 | Feature/Mechanic | Player Health | Player has a health value and will die when it reaches 0. It is displayed in the HUD and can be altered with cheat codes ([L] increases health by 5, [J] decreases health by 5), also regenerates when not on full health | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Camera Target System | Enemy targetting system now automatically target the last hit enemy. - Occlusion objects should be see through | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | Fixed: player doesn't look at target Fixed: Lock on still pulls camera after encounter
2 | Week | 14 | Feature/Mechanic | Combat IFrames | Super cool slowdowns on perfect dodge | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Player Attack | Player can attack with two weapons, and attacks have a hit stop. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Enemy attack indicator | Enemy attack will show an indicator on screen towards the enemy | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | New Attack Timing | Player attacks are timed more reasonably | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Staff heavy hit box | Hit box is resized to fix sometimes not hitting the small enemies. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Weapons | Different weapons and different attacks deal different amount of damage. In addition different weapons apply different knockbacks. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
0 | Divider | 14 |  |  | Level: | 4
2 | Week | 14 | Feature/Mechanic | Art Zoo | Art zoo is stable and running as intended with models displayed. The Zoo UI is removed. use pause menu or cheats to access the scene. | 1.0.0 | Unreal >> Art Zoo |  | Tech | Overruled | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Main Level | New revamped main level, blockout only | 1.0.0 | Unreal >> Play | None | Design | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Environment Skybox | Skybox conveys environment information and matches the environment style. | 1.0.0 | Unreal >> Play | Bryce Fisher | Art | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Animated Holograms | Different weapons and different attacks deal different amount of damage. In addition different weapons apply different knockbacks. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Puddles | Puddles on the ground that reflect light. | 1.0.0 | Unreal >> Play | Bryce Fisher | Art | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Pause Menu Assets | Second pass of Pause Menu assets in the main level. Destructive actions confirmation for both quit and main menu on the pause menu | 1.0.0 | Unreal >> Play | None | Tech | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Option Menu | Option menu should be accessible in Main menu and with Pause Menu, and all functions should work as intended | 1.0.0 | Unreal >> Play | Wei-No Wu | Design | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Lights | Added lights into the main level. | 1.0.0 | Unreal >> Play |  | Design | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Wave Spawn | Fixed Wave spawners that are placed throughout the level and spawns enemy | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Prop Placements | The whole level should have props with reasonable scale and placement. | 1.0.0 | Unreal >> Play | Irene Leung | Design | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Respawn Checkpoints | Respawn Checkpoints has animation when interacted with. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Weapon Models | Weapon Models are implemented and appear in the main level. First pass weapon switch VFX. | 1.0.0 | Unreal >> Play |  | Art | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Lumen | Disabled Lumen | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Ferro Fluid | Main enemies now have ferro fluid effect on them | 1.0.0 | Unreal >> Play |  | Art | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Proper Level Lighting | The new blockout level should have proper lighting so that no spots are too dark | 1.0.0 | Unreal >> Play |  | Art | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Level intro camera sequence | When the level begins, a short camera sequence occurs and pans towards the player. | 1.0.0 | Unreal >> Play | Arthur Wroblewski | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | Fixed: Play can move during opening cutscene
2 | Week | 14 | Content/Asset | Tutorial | Tutorial has updated tutorial texts | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Staff ultimate video | Both weapon types now have the first-pass placeholder ultimate animations. | 1.0.0 | Unreal >> Play |  | Art | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Content/Asset | Combat Locations/Encounters | Combat locations are placed on the tutorial path and is implemented with designers intent. | 1.0.0 | Unreal >> Play |  | Design | Pass | Irene Leung | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Combat Zones/Encounter Zones | Combat zones contain combat walls that activates when players walk into the zone. It should also spawn enemies with customizable field for design use. Final encounter should start after player interacts with glowy call button. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Waypoint | Waypoints are placed in the level to guide the player to the intended area. | 1.0.0 | Unreal >> Play |  | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
0 | Divider | 14 |  |  | Misc: | 4
2 | Week | 14 | Data/Balancing | Cheat System | Updated cheat list is found in the weely build notes | 1.0.0 | Unreal >> Any Level | Lorenzo St. Luce | Tech | Pass | Wei-No Wu |  | Cheats HUD prompt removed
2 | Week | 14 | Feature/Mechanic | Gamepad Support | Full gamepad support works for all gameplay elements and UI | 1.0.0 | Unreal >> Any Level | Dylan Barlow | Tech | Pass | Wei-No Wu | 2025-04-15 20:00 | Fixed: Option sliders don't slide properly on controller.
2 | Week | 14 | Feature/Mechanic | Game Scalability | When player gets into the main level, it automatically scales the graphics. | 1.0.0 | Unreal >> Play | Lorenzo St. Luce | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
2 | Week | 14 | Feature/Mechanic | Performance | Game performance should be optimized and offers variety of settings for lower end machines | 1.0.0 | Unreal >> Play | Lorenzo St. Luce | Tech | Pass | Wei-No Wu | 2025-04-15 20:00
0 | Divider | 13 |  |  | Content/Asset Archive | 6
#REF!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Team Members
David Hedner | Ryder Claus
Lorenzo St. Luce | Dylan Barlow
Avery Steines | Adam Lonstein
Justin Jackson | Arthur Wroblewski
Harley Kirby | Aviral Gusain
Irene Leung | Javi Morales Cortes
Wei-No Wu | Kip George
Dakota Zander
Annika Trautwein
Modem Bumrungkhet
Bryce Fisher
Ethan Chen
Yakshin Vijay